## Item Schedule
Leave Pase III
| Items | UI (ID Name) | Function | API | Ref. UIFlow | manday, 人天 | Priority | Note | Risk
1. Index |  |  | changePageByPanel(pageId) onBackKeyDown() |  |  | 0.5
2. viewPanel |  |  | 1. Connect API: window.GetUserAuthority | GetUserAuthority |  | 0.8
3. viewAgentLeave | Search Agent | searchDept searchEmplID | 1. on("keyup") func: seachDept, searchEmplID 2. Connect API: window.QueryEmployeeData 3. Connect API: window.GetUserAuthority 4. page-mask show() & hide() 5. on("click") func: OK Btn: 重新呼叫API: QueryCalendarData & API: GetDefaultSetting/ 清除Btn | GetUserAuthority QueryEmployeeData | 2-1-1 | 3
4. viewClockin
4.1 | Apply Clock in |  | 1. 出勤Date picker, 班別名稱, 刷卡類型, Date & Time picker, 未刷卡原因, 其他原因 2.checkLeaveBeforePreview 3. on("click") func: #emptyClockinForm 4. on("click") func: #previewBtn:預覽送簽 5. on("click") func: #applyBtn 6. on("click") func: #confirmSend 7. on("blur") func: Date&Time 8. popupMsgInit |  |  | 5
4.2 | Preview Apply |  | 1. Connect API: window.SendModifyAttendanceFormData 2. on("click") func: #backMain | SendModifyAttendanceFormData |  | 3
5. viewOvertimeSubmit
5.1 | Apply Overtime |  | 1. Overtime Date picker, startTime picker, 加班原因 2. Check Working Date and Time&加班時數: API: CountOvertimeHours 3. checkOvertimeBeforePreview 3. on("click") func: #emptyOvertimeForm 4. on("click") func: #previewBtn:預覽送簽 5. on("click") func: #applyBtn 6. on("click") func: #confirmSend 7. on("blur") func: Date&Time 8. popupMsgInit | CountOvertimeHours |  | 5
5.2 | Preview Apply |  | 1. Connect API: window.SendOvertimeFormData 2. on("click") func: #backMain | SendOvertimeFormData |  | 3
6. viewOvertimeQuery
6.1 | Query Overtime List |  | 1. func backOvertimeQueryInit: 加班單初始化 2. func setBackOvertimeList():動態生成HTML 3. func backOvertimeToDetail(btn1, btn2, state) 4. func getBackLeaveDetailByID(id) 5. Connect API: window.QueryEmployeeOvertimeForm 6. on("click") func: queryOvertimeDetail 7. Connect API: window.OvertimeFormDetail 9. on("click") func: #backLeaveSignFlow 10. on("click") func: #signToLeaveDetail | QueryEmployeeOvertimeForm OvertimeFormDetail |  | 5
6.2 | Overtime Detail |  | 1. on("click") func: #backToList 2. on("click") func: #withdrawBackLeaveBtn 3. on("click") func: #backToSign 4. func SignToReason() 5. on("keyup") func: #signTowithdrawReason 6. on("click") func: #signTowithdrawReason/ #confirmWithdrawBackLeave 7. Connect API: window.RecallOvertimeForm 8. on("click") func: #deleteBackLeaveBtn / #comfirmDeleteBackLeave 9. Connect API: window.DeleteOvertimeForm 10.popupMsgInit | OvertimeFormDetailUpdateOvertimeFormRecallOvertimeForm DeleteOvertimeForm |  | 5
7. String Table
7.1 zh-tw String Table | zh-tw String |  | X | X |  | 1
8. Testing | [5 empty] | 4
[5 empty] | 總工時(人天) | 30.3

## Risk Check
Leave Pase III
|  | 1. Index | 2. viewPanel | 3.viewAgentLeave | 4.viewClockin
|  | 1.1 Index | 2.1 viewPanel | 3.1 viewAgentLeave | 4.1 Apply Clock in | 4.2 Preview Apply
1 | Reference | Leave app | Leave app |  | Leave app | Leave app
2 | Input
| Life cycle | pass | pass | check | check | check
3 | Output
| android / ios UI | check | pass | check | check | check
| Localization | check | check | check | check | check
4 | Action
| Repeat | pass | pass | check | check | check
| BigO | pass | pass | check | check | check
| Perfermance | pass | pass | check | check | pass
| Logic | check | check | check | check | check
5 | Other risk | pass | pass | check | check | check
6 | Schedule
| manday(人天） | 0.5 | 0.8 | 3 | 5 | 3
| 5.viewOvertimeSubmit |  |  | 6. viewOvertimeQuery
|  | 5.1 Apply Overtime | 5.2 Preview Apply |  | 6.1 Query Overtime List | 6.2 Overtime Detail
1 | Reference | Leave app | Leave app |  | Leave app | Leave app
2 | Input
| Life cycle | pass | check |  | check | check
3 | Output
| android / ios UI | check | check |  | check | check
| Localization | check | check |  | check | check
4 | Action
| Repeat | check | check |  | check | check
| BigO | check | check |  | check | check
| Perfermance | check | check |  | check | check
| Logic | check | check |  | check | check
5 | Other risk | check | check |  | check | check
6 | Schedule
| manday(人天） | 5 | 3 |  | 5 | 5

## 備註
pass | 略過
check | 需確認畫面/邏輯判斷